## group_information
Group Name | LeaseLink
Usernames | Activity 1 Role | Activity 2 Role | Activity 3 Role | Activity 4 Role
Elizabeth Muya Leiyagu | chairperson | steward | secretary
Joseph Ajak Panchol | steward | scretary | Chairperson
Mathew Macharia | Scribe | chairperson | secretary
Joanne Chepkoech | secretary | scribe | Steward

## learning_objectives
Objective ID | Date | Objective Title | Objective Description | Resources Identified | Other Comments | Group Status | Group Status Comments
1 | 2025-09-14 | Learning HTML Tags | Learn HTML Tags including html, head, body, script and style | Youtube videos |  | 100% | We met and completed HTML
2 | 2025-09-15 | Learning CSS | Learning how to include CSS in HTML including inline, in a style tag or using the link | lecture slides, our notes, and examples from W3schools.com |  | 95% | We finished CSS learning and each understands
3 | 2025-09-16 | Learning JavaScript Basics | Learn how to include JS to display to console, and to change the elements style | lecture slides, and examples from mozilla. |  | 80% | we started and cover most of the concepts
4 | 2025-09-17 | JavaScript intermediary | Using JavaScript to add content to the page (innerHTML, createElement and appendChild) | lecture slides and w3schools.com |  | 50% | We started to discuss but will finish later
5 | 2025-10-04 | JSON Objects | Learn how to write my own json to represent things such as a student, list of students and so on. Then store them and view. |  |  | 80% | Mostly agreed on the JSON content. And later on hardcoded the JSON in the JavaScript file
6 | 2025-10-13 | Learning PHP | variables, echo(print), arrays | Youtube videos and w3school |  | 100% | We met and learn those concepts
7 | 2025-10-17 | Learning PHP intermediate | learning XAMPP, Filezilla, connecting | lecture slides, our notes, and examples from W3schools.com |  | 95% | We finished learning, and each understands

## project_requirements
Objective ID | Date | Objective Title | Objective Description | Resources Identified | Other Comments | Group Status | Group Status Comments
1 | 2025-09-20 | Create HTML page for registration | Build an HTML page for registration using appropriate tags such as <nav>, <section>, <main>, <header>, and <aside>. | Lecture slides, W3Schools examples |  | 100% | Discussions on HTML completed and filenames agreed.
2 | 2025-09-21 | Create HTML form on registration page | Create a registration form using the <form> tag and various input elements. Include labels and placeholders for user guidance | Lecture slides, notes, w3schools example |  | 100% | Discussion on the registration page, including what to have on the forms
3 | 2025-09-25 | Create HML page for registration | Develop a page that displays the results of form submissions. Add an action attribute linking the form to this page. | lecture slides, and examples from youtube |  | 80% | Already discussed
4 | 2025-09-29 | Implement login and registration functionality | Use HTML, CSS, and JavaScript to build interactive login and registration pages. Include form validation. | Lecture slides, MDN documentation, tutorials on JS validation | Team discussed color scheme and layout consistency | 100% | completed and tested locally
5 | 2025-09-30 | Style pages using CSS | Apply internal and external CSS to improve UI consistency and enhance user experience. | W3Schools, CSS-Tricks | CSS reviewed for responsiveness. | 100% | Styling and layout finalized.
6 | 2025-10-01 | Develop Faculty Dashboard | Create a dashboard interface containing sections for “Courses,” “Sessions,” and “Reports.” Include navigation links and placeholders. | Lecture slides, examples youtube | Design planning meeting held. | 80% | The main dashboard layout is complete; features are pending.
7 | 2025-10-02 | Add interactivity to dashboard | Integrate JavaScript to make dashboard pages dynamic (e.g., toggle sections, load content). | Lecture slides and JavaScript videoes | Team tested navigation and session updates. | 90% | Dashboard functions correctly but needs backend integration.
8 | 2025-10-05 | Connect database to dashboard | Connect MySQL database to dashboard to store and retrieve faculty, course, and session data. Test basic CRUD operations | MySQL docs, PHP & XAMPP setup guides | Each member working on their work individually | 100% | Each member successfully established the dashboard connection to the database

## file_guide
Date Agreed | Files | Description | Group Contribution
2025-09-14 | login.html | This will be the landing page | we agreed on how to design and implement the login page
2025-09-14 | registration.html | This is the page for registering a new user, allowing them to create their login credentials. This is the page that handles when a user submits registration | we agreed on how to design and implement the registration page
2025-09-14 | style.css/style2.css | this should be all the style sheets for the login and login form | we agree on the stylings of the login and registration page
2025-10-10 | fi-dashboard.html | This is the page that display the faculty intern dashboard, showcasing the courses, reports and sesssions. | Since activity 02, we agreed to use activity 01 code
2025-10-10 | file.html |  | Since activity 03, we agreed to use activity 02 code
2025-10-14 | script.js | Page containing javascript that will display the information of who has registered | Since activity 03, we agreed to use activity 02 code
2025-10-14 | style.css | our javascript files are here. We will have functions for form_validation(), display_notification() | Since activity 02, we agreed to use the activity 01 code.